## Summary
C06 ME model checks
Run 19 Oct 2026 Reference: the AR model of each building 18 ME models in 14 buildings
5 of 18 ME models need a fix. 1 building has no ME model. 3 models have CAD imports or Generic Models to review.
Check | What is checked | Checked | With issue | Status | What the modeller does
Coordinates | Within 30 m of the reference model of its building, on the shared site | 18 | 5 | FIX | Export the NWC again from Revit on the project shared coordinates
Missing model | Every building that has other models has an ME model | 15 | 1 | FIX | Issue the ME model for the building
Naming | Name is 1104-PAR-<building>-ZZZ-ME-MOD-<number> | 18 | 0 | OK | Nothing to do
File age | NWC saved in the last 7 days | 18 | 0 | OK | Nothing to do
CAD imports | No DWG, IPT or IAM imported into the model | 18 | 3 | REVIEW | Replace each import with a Revit family, or delete it
Generic Models | No family left in the Generic Models category | 18 | 3 | REVIEW | Move each family to its right category, for example Mechanical Equipment
Tabs
Models | one row per ME model, red where a check failed
To fix | one row per thing to fix, High first, with the words to send the modeller
Element IDs | one element per row. Filter on Model, copy the IDs, then Revit Manage > Select by ID
Where a building has no AR model, the EL model is the reference (1B06WL). Where it has no AR or EL, the ME model is (1B06M1, 1B06PK, 1C06M2).

## Models
C06 ME models
One row per model. Red: fix before the next clash run. Amber: review. Grey: nothing to do.
Building | Model | Status | Compared with | Off the reference (m) | Naming | File age (days) | CAD imports (files) | Generic Models (elements) | File name
1B06BC | ME-000001 | OK | AR | under 1 | OK | 2 | 0 | 0 | 1104-PAR-1B06BC-ZZZ-ME-MOD-000001.nwc
1B06G1 | ME-000001 | OK | AR | under 1 | OK | 2 | 0 | 0 | 1104-PAR-1B06G1-ZZZ-ME-MOD-000001.nwc
1B06K1 | ME-000001 | OK | AR | under 1 | OK | 2 | 0 | 0 | 1104-PAR-1B06K1-ZZZ-ME-MOD-000001.nwc
1B06M1 | ME-000001 | OK | itself | reference | OK | 2 | 0 | 0 | 1104-PAR-1B06M1-ZZZ-ME-MOD-000001.nwc
1B06P1 | ME-000001 | OK | AR | under 1 | OK | 2 | 0 | 0 | 1104-PAR-1B06P1-ZZZ-ME-MOD-000001.nwc
1B06PE | ME-000001 | OK | AR | 7.16 | OK | 2 | 0 | 0 | 1104-PAR-1B06PE-ZZZ-ME-MOD-000001.nwc
1B06PH | ME-000001 | OK | AR | 8.11 | OK | 2 | 0 | 0 | 1104-PAR-1B06PH-ZZZ-ME-MOD-000001.nwc
1B06PH | ME-000002 | FIX | AR | 118.682 | OK | 2 | 2 | 1 | 1104-PAR-1B06PH-ZZZ-ME-MOD-000002.nwc
1B06PK | ME-000004 | OK | itself | reference | OK | 2 | 0 | 0 | 1104-PAR-1B06PK-ZZZ-ME-MOD-000004.nwc
1B06PO | ME-000001 | OK | AR | 4.36 | OK | 2 | 0 | 0 | 1104-PAR-1B06PO-ZZZ-ME-MOD-000001.nwc
1B06PP | ME-000001 | OK | AR | under 1 | OK | 2 | 0 | 0 | 1104-PAR-1B06PP-ZZZ-ME-MOD-000001.nwc
1B06PP | ME-000002 | FIX | AR | 255.238 | OK | 2 | 0 | 0 | 1104-PAR-1B06PP-ZZZ-ME-MOD-000002.nwc
1B06PP | ME-000003 | FIX | AR | 328.335 | OK | 2 | 4 | 38 | 1104-PAR-1B06PP-ZZZ-ME-MOD-000003.nwc
1B06PS | none | MISSING | [6 empty] | No ME model. This building has AR, EL and ST.
1B06WL | ME-000001 | FIX | EL | 30.215 | OK | 2 | 0 | 0 | 1104-PAR-1B06WL-ZZZ-ME-MOD-000001.nwc
1B06WL | ME-000002 | FIX | EL | 30.215 | OK | 2 | 1 | 1 | 1104-PAR-1B06WL-ZZZ-ME-MOD-000002.nwc
1B06WM | ME-000001 | OK | AR | 1.21 | OK | 2 | 0 | 0 | 1104-PAR-1B06WM-ZZZ-ME-MOD-000001.nwc
1B06WO | ME-000001 | OK | AR | 1.85 | OK | 2 | 0 | 0 | 1104-PAR-1B06WO-ZZZ-ME-MOD-000001.nwc
1C06M2 | ME-000001 | OK | itself | reference | OK | 2 | 0 | 0 | 1104-PAR-1C06M2-ZZZ-ME-MOD-000001.nwc

## To fix
C06 ME to fix
One row per thing to fix. High first. Send the Fix words to the modeller as they are.
No. | Priority | Building | Model | Check | Finding | Value | Unit | Fix
1 | High | 1B06PH | ME-000002 | Coordinates | 118.7 m from the AR model. ME on site ARD_PW_CHLOR BUILDING, AR on PWPS_Shared_Location | 118.682 | m | Export the NWC again on the project shared coordinates
2 | High | 1B06PP | ME-000002 | Coordinates | 255.2 m from the AR model. ME on site 16-S01, AR on IRPS-SharedCoordinate | 255.238 | m | Export the NWC again on the project shared coordinates
3 | High | 1B06PP | ME-000003 | Coordinates | 328.3 m from the AR model. ME on site 16-S01, AR on IRPS-SharedCoordinate | 328.335 | m | Export the NWC again on the project shared coordinates
4 | High | 1B06PS | none | Missing model | No ME model. AR, EL and ST are issued |  |  | Issue the ME model for this building
5 | High | 1B06WL | ME-000001 | Coordinates | 30.2 m from the EL model. ME on site PW3_Shared_Location, EL on IGN2 | 30.215 | m | Export the NWC again on the project shared coordinates
6 | High | 1B06WL | ME-000002 | Coordinates | 30.2 m from the EL model. ME on site SWLS-02 MECH, EL on IGN2 | 30.215 | m | Export the NWC again on the project shared coordinates
7 | Low | 1B06PH | ME-000002 | CAD import | Imported Chem-Feed Pkg-R0.dwg | 2 | elements | Replace with a Revit family, or delete it
8 | Low | 1B06PH | ME-000002 | CAD import | Imported Chlorine Transfer pump.dwg | 1 | element | Replace with a Revit family, or delete it
9 | Low | 1B06PH | ME-000002 | Generic Models | Family MEC-GEN-Base-PAR, type SPAL- MECH EQ -Base | 1 | element | Move the family to its right category
10 | Low | 1B06PP | ME-000003 | CAD import | Imported sewage-pump.dwg | 2 | elements | Replace with a Revit family, or delete it
11 | Low | 1B06PP | ME-000003 | CAD import | Imported AIR VENT 100mm.dwg | 3 | elements | Replace with a Revit family, or delete it
12 | Low | 1B06PP | ME-000003 | CAD import | Imported FAB200-25RF.iam | 3 | elements | Replace with a Revit family, or delete it
13 | Low | 1B06PP | ME-000003 | CAD import | Imported O_859_00_DN500_1XXXX00_AA0.ipt | 2 | elements | Replace with a Revit family, or delete it
14 | Low | 1B06PP | ME-000003 | Generic Models | Family PAR-ME-GEN-PSN_STEPS_LADDER, type Ladder | 2 | elements | Move the family to its right category
15 | Low | 1B06PP | ME-000003 | Generic Models | Family PAR-ME-GEN-SPAL- MECH EQ -Base, type SPAL- MECH EQ -Base | 36 | elements | Move the family to its right category
16 | Low | 1B06WL | ME-000002 | CAD import | Imported Air Vent Valve.dwg | 2 | elements | Replace with a Revit family, or delete it
17 | Low | 1B06WL | ME-000002 | Generic Models | Family PAR-ME-GEN-MECH EQ Base, type SPAL- MECH EQ -Base | 1 | element | Move the family to its right category

## Element IDs
C06 ME element IDs
One element per row. Filter on Model, copy the Element ID cells, then in Revit: Manage > Select by ID.
Building | Model | Check | CAD file or family | Type | Element ID
1B06PH | ME-000002 | CAD import | Chem-Feed Pkg-R0.dwg |  | 1819523
1B06PH | ME-000002 | CAD import | Chem-Feed Pkg-R0.dwg |  | 1819548
1B06PH | ME-000002 | CAD import | Chlorine Transfer pump.dwg |  | 1819614
1B06PH | ME-000002 | Generic Models | MEC-GEN-Base-PAR | SPAL- MECH EQ -Base | 2116825
1B06PP | ME-000003 | CAD import | sewage-pump.dwg |  | 6489702
1B06PP | ME-000003 | CAD import | sewage-pump.dwg |  | 6489717
1B06PP | ME-000003 | CAD import | AIR VENT 100mm.dwg |  | 6489731
1B06PP | ME-000003 | CAD import | AIR VENT 100mm.dwg |  | 6500078
1B06PP | ME-000003 | CAD import | AIR VENT 100mm.dwg |  | 6500080
1B06PP | ME-000003 | CAD import | FAB200-25RF.iam |  | 6490236
1B06PP | ME-000003 | CAD import | FAB200-25RF.iam |  | 6490320
1B06PP | ME-000003 | CAD import | FAB200-25RF.iam |  | 6490363
1B06PP | ME-000003 | CAD import | O_859_00_DN500_1XXXX00_AA0.ipt |  | 6499998
1B06PP | ME-000003 | CAD import | O_859_00_DN500_1XXXX00_AA0.ipt |  | 6500053
1B06PP | ME-000003 | Generic Models | PAR-ME-GEN-PSN_STEPS_LADDER | Ladder | 6525287
1B06PP | ME-000003 | Generic Models | PAR-ME-GEN-PSN_STEPS_LADDER | Ladder | 6525298
1B06PP | ME-000003 | Generic Models | PAR-ME-GEN-SPAL- MECH EQ -Base | SPAL- MECH EQ -Base | 6490135
1B06PP | ME-000003 | Generic Models | PAR-ME-GEN-SPAL- MECH EQ -Base | SPAL- MECH EQ -Base | 6490296
1B06PP | ME-000003 | Generic Models | PAR-ME-GEN-SPAL- MECH EQ -Base | SPAL- MECH EQ -Base | 6490298
1B06PP | ME-000003 | Generic Models | PAR-ME-GEN-SPAL- MECH EQ -Base | SPAL- MECH EQ -Base | 6490342
1B06PP | ME-000003 | Generic Models | PAR-ME-GEN-SPAL- MECH EQ -Base | SPAL- MECH EQ -Base | 6490382
1B06PP | ME-000003 | Generic Models | PAR-ME-GEN-SPAL- MECH EQ -Base | SPAL- MECH EQ -Base | 6490384
1B06PP | ME-000003 | Generic Models | PAR-ME-GEN-SPAL- MECH EQ -Base | SPAL- MECH EQ -Base | 6490389
1B06PP | ME-000003 | Generic Models | PAR-ME-GEN-SPAL- MECH EQ -Base | SPAL- MECH EQ -Base | 6490391
1B06PP | ME-000003 | Generic Models | PAR-ME-GEN-SPAL- MECH EQ -Base | SPAL- MECH EQ -Base | 6527341
1B06PP | ME-000003 | Generic Models | PAR-ME-GEN-SPAL- MECH EQ -Base | SPAL- MECH EQ -Base | 6527468
1B06PP | ME-000003 | Generic Models | PAR-ME-GEN-SPAL- MECH EQ -Base | SPAL- MECH EQ -Base | 6527471
1B06PP | ME-000003 | Generic Models | PAR-ME-GEN-SPAL- MECH EQ -Base | SPAL- MECH EQ -Base | 6533033
1B06PP | ME-000003 | Generic Models | PAR-ME-GEN-SPAL- MECH EQ -Base | SPAL- MECH EQ -Base | 6533090
1B06PP | ME-000003 | Generic Models | PAR-ME-GEN-SPAL- MECH EQ -Base | SPAL- MECH EQ -Base | 6533183
1B06PP | ME-000003 | Generic Models | PAR-ME-GEN-SPAL- MECH EQ -Base | SPAL- MECH EQ -Base | 6533197
1B06PP | ME-000003 | Generic Models | PAR-ME-GEN-SPAL- MECH EQ -Base | SPAL- MECH EQ -Base | 6533311
1B06PP | ME-000003 | Generic Models | PAR-ME-GEN-SPAL- MECH EQ -Base | SPAL- MECH EQ -Base | 6533319
1B06PP | ME-000003 | Generic Models | PAR-ME-GEN-SPAL- MECH EQ -Base | SPAL- MECH EQ -Base | 6533327
1B06PP | ME-000003 | Generic Models | PAR-ME-GEN-SPAL- MECH EQ -Base | SPAL- MECH EQ -Base | 6533335
1B06PP | ME-000003 | Generic Models | PAR-ME-GEN-SPAL- MECH EQ -Base | SPAL- MECH EQ -Base | 6612244
1B06PP | ME-000003 | Generic Models | PAR-ME-GEN-SPAL- MECH EQ -Base | SPAL- MECH EQ -Base | 6612275
1B06PP | ME-000003 | Generic Models | PAR-ME-GEN-SPAL- MECH EQ -Base | SPAL- MECH EQ -Base | 6612484
1B06PP | ME-000003 | Generic Models | PAR-ME-GEN-SPAL- MECH EQ -Base | SPAL- MECH EQ -Base | 6612492
1B06PP | ME-000003 | Generic Models | PAR-ME-GEN-SPAL- MECH EQ -Base | SPAL- MECH EQ -Base | 6612502
1B06PP | ME-000003 | Generic Models | PAR-ME-GEN-SPAL- MECH EQ -Base | SPAL- MECH EQ -Base | 6612919
1B06PP | ME-000003 | Generic Models | PAR-ME-GEN-SPAL- MECH EQ -Base | SPAL- MECH EQ -Base | 6613251
1B06PP | ME-000003 | Generic Models | PAR-ME-GEN-SPAL- MECH EQ -Base | SPAL- MECH EQ -Base | 6613261
1B06PP | ME-000003 | Generic Models | PAR-ME-GEN-SPAL- MECH EQ -Base | SPAL- MECH EQ -Base | 6613273
1B06PP | ME-000003 | Generic Models | PAR-ME-GEN-SPAL- MECH EQ -Base | SPAL- MECH EQ -Base | 6613283
1B06PP | ME-000003 | Generic Models | PAR-ME-GEN-SPAL- MECH EQ -Base | SPAL- MECH EQ -Base | 6613293
1B06PP | ME-000003 | Generic Models | PAR-ME-GEN-SPAL- MECH EQ -Base | SPAL- MECH EQ -Base | 6499972
1B06PP | ME-000003 | Generic Models | PAR-ME-GEN-SPAL- MECH EQ -Base | SPAL- MECH EQ -Base | 6499985
1B06PP | ME-000003 | Generic Models | PAR-ME-GEN-SPAL- MECH EQ -Base | SPAL- MECH EQ -Base | 6500075
1B06PP | ME-000003 | Generic Models | PAR-ME-GEN-SPAL- MECH EQ -Base | SPAL- MECH EQ -Base | 6500076
1B06PP | ME-000003 | Generic Models | PAR-ME-GEN-SPAL- MECH EQ -Base | SPAL- MECH EQ -Base | 6500319
1B06PP | ME-000003 | Generic Models | PAR-ME-GEN-SPAL- MECH EQ -Base | SPAL- MECH EQ -Base | 6500329
1B06WL | ME-000002 | CAD import | Air Vent Valve.dwg |  | 2973244
1B06WL | ME-000002 | CAD import | Air Vent Valve.dwg |  | 3819014
1B06WL | ME-000002 | Generic Models | PAR-ME-GEN-MECH EQ Base | SPAL- MECH EQ -Base | 4047214